## Summary
EOW State Pages: Work Report
expertophthalmologywitness.com ¦ Content and on-page SEO update of the state and location pages (no redesign)
Website | https://www.expertophthalmologywitness.com/
Scope | Content-only update of the state and location pages. Design, header, footer and page URLs stay the same.
Target keywords | expert ophthalmology witness {state} ¦ expert ophthalmologist witness {state}
Sample page | Kentucky
Kentucky review page (Before / After / What changed) | https://kunaldabiseo.github.io/eow-website/kentucky/
Kentucky updated page (draft) | https://kunaldabiseo.github.io/eow-website/kentucky/updated-page.html
Kentucky live page (not yet updated) | https://www.expertophthalmologywitness.com/kentucky-expert-ophthalmology-witness/
Full report (README) | https://github.com/kunaldabiseo/eow-website/tree/main/kentucky
Status at a glance
Location pages on the site | 45
US states + DC with a page | 40
International / territory pages | 5
Pages with the same body text (only state name changes) | 45
Pages using "ophthalmologist" in the body text | 0
Pages updated (draft ready) | 1
Pages live with the update | 0
Pages not started | 44
US states with no page yet | 11
Client feedback items done | 7
Client feedback items open | 2
Questions waiting for a client answer | 5
Sheets in this workbook
State Pages | Every location page with its current title, meta description, word count and the issues found.
Kentucky Changes | Every change on the Kentucky sample page: before, after and the reason.
Feedback Tracker | Each feedback item from the review and where it stands.
Fact Check | Every fact and figure on the Kentucky page and the source it was checked against.
Open Questions | Points that need a decision from you.
Missing States | US states with no page on the site yet.
Counts in "Status at a glance" are formulas and update when the Status column on the State Pages sheet changes.

## State Pages
State and Location Pages
Audit of every location page in the sitemap (page-sitemap.xml). Status values: Not started / Draft ready, awaiting go-live / Live
# | Location | Type | Live URL | Current title | Title length | Current meta description | Meta length | "ophthalmologist" in body | Same body text as other pages | Issues found | Status | Review / demo URL
1 | Alabama | US state / DC | https://www.expertophthalmologywitness.com/alabama-expert-ophthalmology-witness/ | Alabama Expert Ophthalmology Witness | 36 | Alabama Expert Ophthalmology Witness Testimony, Alabama Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
2 | Alaska | US state / DC | https://www.expertophthalmologywitness.com/alaska-expert-ophthalmology-witness/ | Alaska Expert Ophthalmology Witness | 35 | Alaska Expert Ophthalmology Witness Testimony, Alaska Expert Ophthalmologist Witness Testimony | 94 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
3 | Arizona | US state / DC | https://www.expertophthalmologywitness.com/arizona-expert-ophthalmology-witness/ | Arizona Expert Ophthalmology Witness | 36 | Arizona Expert Ophthalmology Witness Testimony, Arizona Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
4 | California | US state / DC | https://www.expertophthalmologywitness.com/california-expert-ophthalmology-witness/ | California Expert Ophthalmology Witness | 39 | California Expert Ophthalmology Witness Testimony, California Expert Ophthalmologist Witness Testimony | 102 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
5 | Canada | International / territory | https://www.expertophthalmologywitness.com/canada-expert-ophthalmology-witness/ | Canada Expert Ophthalmology Witness | 35 | Canada Expert Ophthalmology Witness Testimony, case review, deposition, litigation support for plaintiff & defense. Canada Expert Ophthalmologist Witness Testimony | 163 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description too long (163 characters, cut off in Google) • In-text "Refractive surgery" link goes through a redirect | Not started
6 | Colorado | US state / DC | https://www.expertophthalmologywitness.com/colorado-expert-ophthalmology-witness/ | Colorado Expert Ophthalmology Witness | 37 | Colorado Expert Ophthalmology Witness Testimony, Colorado Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
7 | Connecticut | US state / DC | https://www.expertophthalmologywitness.com/connecticut-expert-ophthalmology-witness/ | Connecticut Expert Ophthalmology Witness | 40 | Connecticut Expert Ophthalmology Witness Testimony, Connecticut Expert Ophthalmologist Witness Testimony | 104 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
8 | District of Columbia | US state / DC | https://www.expertophthalmologywitness.com/district-of-columbia-expert-ophthalmology-witness/ | District of Columbia Expert Ophthalmology Witness | 49 | District of Columbia Expert Ophthalmology Witness Testimony, District of Columbia Expert Ophthalmologist Witness Testimony | 122 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
9 | Florida | US state / DC | https://www.expertophthalmologywitness.com/florida-expert-ophthalmology-witness/ | Florida Expert Ophthalmology Witness ¦ Dr. Todd Lefkowitz | 57 | Florida Expert Ophthalmology Witness Testimony, Florida Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
10 | Georgia | US state / DC | https://www.expertophthalmologywitness.com/georgia-expert-ophthalmology-witness/ | Georgia Expert Ophthalmology Witness | 36 | Georgia Expert Ophthalmology Witness Testimony, Georgia Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
11 | Hawaii | US state / DC | https://www.expertophthalmologywitness.com/hawaii-expert-ophthalmology-witness/ | Hawaii Expert Ophthalmology Witness | 35 | Hawaii Expert Ophthalmology Witness Testimony, Hawaii Expert Ophthalmologist Witness Testimony | 94 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
12 | Idaho | US state / DC | https://www.expertophthalmologywitness.com/idaho-expert-ophthalmology-witness/ | Idaho Expert Ophthalmology Witness | 34 | Idaho Expert Ophthalmology Witness Testimony, Idaho Expert Ophthalmologist Witness Testimony | 92 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
13 | Illinois | US state / DC | https://www.expertophthalmologywitness.com/illinois-expert-ophthalmology-witness/ | Illinois Expert Ophthalmology Witness | 37 | Illinois Expert Ophthalmology Witness Testimony, Illinois Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
14 | Indiana | US state / DC | https://www.expertophthalmologywitness.com/indiana-expert-ophthalmology-witness/ | Indiana Expert Ophthalmology Witness | 36 | Indiana Expert Ophthalmology Witness Testimony, Indiana Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
15 | Kansas | US state / DC | https://www.expertophthalmologywitness.com/kansas-expert-ophthalmology-witness/ | Kansas Expert Ophthalmology Witness | 35 | Kansas Expert Ophthalmology Witness Testimony, Kansas Expert Ophthalmologist Witness Testimony | 94 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
16 | Kentucky | US state / DC | https://www.expertophthalmologywitness.com/kentucky-expert-ophthalmology-witness/ | Kentucky Expert Ophthalmology Witness | 37 | Kentucky Expert Ophthalmology Witness, Kentucky Expert Ophthalmologist Witness Testimony | 88 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Draft ready, awaiting go-live | https://kunaldabiseo.github.io/eow-website/kentucky/
17 | Louisiana | US state / DC | https://www.expertophthalmologywitness.com/louisiana-expert-ophthalmology-witness/ | Louisiana Expert Ophthalmology Witness | 38 | Louisiana Expert Ophthalmology Witness Testimony, Louisiana Expert Ophthalmologist Witness Testimony | 100 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
18 | Massachusetts | US state / DC | https://www.expertophthalmologywitness.com/massachusetts-expert-ophthalmology-witness/ | Massachusetts Expert Ophthalmology Witness | 42 | Massachusetts Expert Ophthalmology Witness Testimony, Massachusetts Expert Ophthalmologist Witness Testimony | 108 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
19 | Michigan | US state / DC | https://www.expertophthalmologywitness.com/michigan-expert-ophthalmology-witness/ | Michigan Expert Ophthalmology Witness | 37 | Michigan Expert Ophthalmology Witness Testimony, Michigan Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
20 | Minnesota | US state / DC | https://www.expertophthalmologywitness.com/minnesota-expert-ophthalmology-witness/ | Minnesota Expert Ophthalmology Witness | 38 | Minnesota Expert Ophthalmology Witness Testimony, Minnesota Expert Ophthalmologist Witness Testimony | 100 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
21 | Mississippi | US state / DC | https://www.expertophthalmologywitness.com/mississippi-expert-ophthalmology-witness/ | Mississippi Expert Ophthalmology Witness | 40 | Mississippi Expert Ophthalmology Witness Testimony, Mississippi Expert Ophthalmologist Witness Testimony | 104 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
22 | Missouri | US state / DC | https://www.expertophthalmologywitness.com/missouri-expert-ophthalmology-witness/ | Missouri Expert Ophthalmology Witness | 37 | Missouri Expert Ophthalmology Witness Testimony, Missouri Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
23 | Montana | US state / DC | https://www.expertophthalmologywitness.com/montana-expert-ophthalmology-witness/ | Montana Expert Ophthalmology Witness | 36 | Montana Expert Ophthalmology Witness Testimony, Montana Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
24 | Nevada | US state / DC | https://www.expertophthalmologywitness.com/nevada-expert-ophthalmology-witness/ | Nevada Expert Ophthalmology Witness | 35 | Nevada Expert Ophthalmology Witness Testimony, Nevada Expert Ophthalmologist Witness Testimony | 94 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
25 | New Jersey | US state / DC | https://www.expertophthalmologywitness.com/new-jersey-expert-ophthalmology-witness/ | New Jersey Expert Ophthalmology Witness | 39 | New Jersey Expert Ophthalmology Witness Testimony, New Jersey Expert Ophthalmologist Witness Testimony | 102 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
26 | New Mexico | US state / DC | https://www.expertophthalmologywitness.com/new-mexico-expert-ophthalmology-witness/ | New Mexico Expert Ophthalmology Witness | 39 | New Mexico Expert Ophthalmology Witness Testimony, New Mexico Expert Ophthalmologist Witness Testimony | 102 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
27 | New York | US state / DC | https://www.expertophthalmologywitness.com/new-york-expert-ophthalmology-witness/ | New York Expert Ophthalmology Witness | 37 | New York Expert Ophthalmology Witness Testimony, New York Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
28 | North Carolina | US state / DC | https://www.expertophthalmologywitness.com/north-carolina-expert-ophthalmology-witness/ | North Carolina Expert Ophthalmology Witness | 43 | North Carolina Expert Ophthalmology Witness Testimony, North Carolina Expert Ophthalmologist Witness Testimony | 110 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
29 | Ohio | US state / DC | https://www.expertophthalmologywitness.com/ohio-expert-ophthalmology-witness/ | Ohio Expert Ophthalmology Witness | 33 | Ohio Expert Ophthalmology Witness Testimony, Ohio Expert Ophthalmologist Witness Testimony | 90 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
30 | Oklahoma | US state / DC | https://www.expertophthalmologywitness.com/oklahoma-expert-ophthalmology-witness/ | Oklahoma Expert Ophthalmology Witness | 37 | Oklahoma Expert Ophthalmology Witness Testimony, Oklahoma Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
31 | Oregon | US state / DC | https://www.expertophthalmologywitness.com/oregon-expert-ophthalmology-witness/ | Oregon Expert Ophthalmology Witness | 35 | Oregon Expert Ophthalmology Witness Testimony, case review, deposition, litigation support for plaintiff & defense. Oregon Expert Ophthalmologist Witness Testimony | 163 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description too long (163 characters, cut off in Google) • In-text "Refractive surgery" link goes through a redirect | Not started
32 | Pennsylvania | US state / DC | https://www.expertophthalmologywitness.com/pennsylvania-expert-ophthalmology-witness/ | Pennsylvania Expert Ophthalmology Witness | 41 | Pennsylvania Expert Ophthalmology Witness Testimony, Pennsylvania Expert Ophthalmologist Witness Testimony | 106 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
33 | Puerto Rico | International / territory | https://www.expertophthalmologywitness.com/puerto-rico-expert-ophthalmology-witness/ | Puerto Rico Expert Ophthalmology Witness | 40 | Puerto Rico Expert Ophthalmology Witness Testimony, case review, deposition, litigation support for plaintiff & defense. Puerto Rico Expert Ophthalmologist Witness Testimony | 173 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description too long (173 characters, cut off in Google) • In-text "Refractive surgery" link goes through a redirect | Not started
34 | Rhode Island | US state / DC | https://www.expertophthalmologywitness.com/rhose-island-expert-ophthalmology-witness-dr-todd-lefkowitz/ | Rhode Island Expert Ophthalmology Witness | 41 | Rhode Island Expert Ophthalmology Witness Testimony, for Plaintiff and Defense. Deposition, Trial and Case Reviews. | 115 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • URL typo: "rhose-island" • URL pattern differs from the other location pages • In-text "Refractive surgery" link goes through a redirect | Not started
35 | South Africa | International / territory | https://www.expertophthalmologywitness.com/south-africa-expert-ophthalmology-witness/ | South Africa Expert Ophthalmology Witness – DR. Todd Lefkowitz | 62 | Dr. Lefkowitz provides South Africa Expert Ophthalmology Witness services for medicolega cases in South Africa and worldwide. Dr Lefkowitz specializes in: Cataract Surgery, Eyelid surgery, Refractive | 199 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description too long (199 characters, cut off in Google) • Typo in meta description: "medicolega" • Title uses "DR." in capitals • In-text "Refractive surgery" link goes through a redirect | Not started
36 | South Dakota | US state / DC | https://www.expertophthalmologywitness.com/south-dakota-expert-ophthalmology-witness/ | South Dakota Expert Ophthalmology Witness | 41 | South Dakota Expert Ophthalmology Witness Testimony, South Dakota Expert Ophthalmologist Witness Testimony | 106 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
37 | Tennessee | US state / DC | https://www.expertophthalmologywitness.com/tennessee-expert-ophthalmology-witness/ | Tennessee Expert Ophthalmology Witness | 38 | Tennessee Expert Ophthalmology Witness Testimony, Tennessee Expert Ophthalmologist Witness Testimony | 100 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
38 | Texas | US state / DC | https://www.expertophthalmologywitness.com/texas-expert-ophthalmology-witness/ | Texas Expert Ophthalmology Witness | 34 | Texas Expert Ophthalmology Witness Testimony, Texas Expert Ophthalmologist Witness Testimony | 92 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
39 | US Virgin Islands | International / territory | https://www.expertophthalmologywitness.com/us-virgin-islands-expert-ophthalmology-witness/ | US Virgin Islands Expert Ophthalmology Witness – DR. Todd Lefkowitz | 67 | Dr. Lefkowitz provides Expert Ophthalmology Witness services for medicolega cases in The US Virgin Islands and worldwide. Dr Lefkowitz specializes in: Cataract Surgery, Eyelid surgery, Refractive sur… | 200 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description too long (200 characters, cut off in Google) • Typo in meta description: "medicolega" • Title uses "DR." in capitals • In-text "Refractive surgery" link goes through a redirect | Not started
40 | United Kingdom | International / territory | https://www.expertophthalmologywitness.com/united-kingdom-expert-ophthalmology-witness/ | United Kingdom Expert Ophthalmology Witness – DR. Todd Lefkowitz | 64 | Dr. Lefkowitz provides Expert Ophthalmology Witness services for medicolega cases in The United Kingdom and worldwide. Dr Lefkowitz specializes in: Cataract Surgery, Eyelid surgery, Refractive surger… | 200 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description too long (200 characters, cut off in Google) • Typo in meta description: "medicolega" • Title uses "DR." in capitals • In-text "Refractive surgery" link goes through a redirect | Not started
41 | Utah | US state / DC | https://www.expertophthalmologywitness.com/utah-expert-ophthalmology-witness/ | Utah Expert Ophthalmology Witness | 33 | Utah Expert Ophthalmology Witness Testimony, Utah Expert Ophthalmologist Witness Testimony | 90 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
42 | Virginia | US state / DC | https://www.expertophthalmologywitness.com/virginia-expert-ophthalmology-witness/ | Virginia Expert Ophthalmology Witness | 37 | Virginia Expert Ophthalmology Witness Testimony, Virginia Expert Ophthalmologist Witness Testimony | 98 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
43 | Washington | US state / DC | https://www.expertophthalmologywitness.com/washington-expert-ophthalmology-witness/ | Washington Expert Ophthalmology Witness | 39 | Washington Expert Ophthalmology Witness Testimony, Washington Expert Ophthalmologist Witness Testimony | 102 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
44 | West Virginia | US state / DC | https://www.expertophthalmologywitness.com/west-virginia-expert-ophthalmology-witness/ | West Virginia Expert Ophthalmology Witness | 42 | West Virginia Expert Ophthalmology Witness Testimony, West Virginia Expert Ophthalmologist Witness Testimony | 108 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • In-text "Refractive surgery" link goes through a redirect | Not started
45 | Wyoming | US state / DC | https://www.expertophthalmologywitness.com/wyoming-expert-ophthalmology-witness-dr-todd-lefkowitz/ | Wyoming Expert Ophthalmology Witness | 36 | Wyoming Expert Ophthalmology Witness Testimony, Wyoming Expert Ophthalmologist Witness Testimony | 96 | 0 | Yes | • Same body text as every other location page (only the location name changes) • "ophthalmologist" keyword not used in the body text • Only template H2 headings, nothing about the location • No location-specific facts (rules, courts, cases) • Images have no alt text • Share image (og:image) is the email icon • Meta description is a keyword list, not a sentence • URL pattern differs from the other location pages • In-text "Refractive surgery" link goes through a redirect | Not started
Title length and meta length are formulas (=LEN). Audit taken from the live site on 23 Oct 2026.

## Kentucky Changes
Kentucky Sample Page: Before and After
Design stays the same. Review all changes side by side at https://kunaldabiseo.github.io/eow-website/kentucky/
Item | Before (live page) | After (updated page) | Why
Search title | Kentucky Expert Ophthalmology Witness | Kentucky Expert Ophthalmology Witness ¦ Dr. Todd Lefkowitz MD | Adds Dr. Lefkowitz's name so the result reads as a real practice.
Meta description | Kentucky Expert Ophthalmology Witness, Kentucky Expert Ophthalmologist Witness Testimony | Expert ophthalmologist witness for Kentucky cases. Board-certified Dr. Todd Lefkowitz reviews eye surgery claims, mainly for plaintiff and sometimes defense. | A full sentence instead of a keyword list, with the "ophthalmologist" keyword.
Main heading (H1) | Kentucky Expert Ophthalmology Witness – Dr. Todd Lefkowitz | No change | Already correct.
Body content | 236 words, same text as every other location page | About 840 words written for Kentucky | Unique content gives the page its own reason to rank for Kentucky.
"ophthalmologist" keyword | Not used in the body | Used in the opening, a section heading and the meta description | Covers both search terms.
Section headings (H2) | Only the shared site headings | 8 Kentucky sections: services, Kentucky rules, case types, credentials, how to start, FAQs, nearby states | Clear structure for readers and search engines.
Kentucky rules | Not mentioned | Certificate of merit (KRS 411.167) and one-year filing limit (KRS 413.140), each linked to the official statute | Shows the page is written for Kentucky cases.
Credentials | One general sentence | Board certification, Arizona Medical Board roles, MAXIMUS, teaching post, Air Force service, liability record, each linked to the About page | All taken from the existing About page.
FAQs | None | 4 questions in a one-at-a-time accordion | Answers common attorney questions.
How to start | One sentence | 3 steps: email or contact form, talk through the case, send the records | Clear next step for an attorney.
Internal links | Refractive link went through a redirect; keyword link went to the homepage | Refractive link fixed; links to the main expert witness page, retinal detachment page and 7 neighbouring states | Helps visitors and search engines move between related pages.
Source links | None | Every statute, date and figure links to its source | Requested in the review.
Structured data (schema) | Basic page data only | Service, Person, Organization, FAQ, HowTo, Breadcrumb, Legislation, State, Image, matched to the visible text | Helps Google and AI search tools understand the page.
Share image | Email icon | Dr. Lefkowitz's photo | His photo shows when the link is shared.
Sidebar (desktop) | Scrolls away | Stays in view while the content scrolls | Photo and expertise links stay visible.
Spelling | "Affadavits", "court room" | Corrected

## Feedback Tracker
Review Feedback Tracker
Status values: Done / Open
# | Date | Feedback | What was done | Status
1 | 24 Oct 2026 | Any stat like this needs to be linked to the source | Every statute, date and figure on the page now links to its source (official Kentucky statutes, About page, main expert witness page). | Done
2 | 28 Oct 2026 | Edit: "Affidavits in support of your case" → "...if merited" | Applied. | Done
3 | 28 Oct 2026 | Edit: "He understands that some cases are time sensitive..." → "Dr. Lefkowitz understands... Once the case is received..." | Applied. | Done
4 | 28 Oct 2026 | Edit: "ophthalmology review early" → "expert ophthalmology witness review early" | Applied. | Done
5 | 28 Oct 2026 | Edit: step 3 → "Send Dr. Lefkowitz the medical records. He will review them and provide an expert ophthalmology witness report with his opinion." | Applied, in the page and in the structured data. | Done
6 | 28 Oct 2026 | Edit: FAQ answer → "mainly plaintiff and sometimes defense counsel" | Applied. The same wording is now used in the opening paragraph, meta description and structured data. | Done
7 | 28 Oct 2026 | Double / triple check all stats and details | Every fact and figure checked against the About page, the main expert witness page and the official statute text (see Fact Check). Three case-type details not supported by the site were removed. | Done
8 | 28 Oct 2026 | Complete the Kentucky page and send the final live URL | Waiting on the case count answer (see Open Questions) before publishing. | Open
9 | 28 Oct 2026 | Apply the notes to all other state pages and send Dev/Demo URLs | Next step after the Kentucky page. | Open

## Fact Check
Fact Check: Kentucky Page
Every fact and figure on the updated page and the source it was checked against
Fact on the page | Section | Checked against | Source link | Result
Diplomate, American Board of Ophthalmology since 1982 | Credentials | About page: "Diplomate, American Board of Ophthalmology Dec. 1982" | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Over 40 years of practice as a surgeon and clinician | Credentials | About page: "over 40 years of practical experience; he is a surgeon and clinician" | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Expert reviewer for the Arizona Medical Board 2000 to 2007 | Credentials | About page: "Outside Ophthalmology Consultant, Arizona Medical Board, 2000-2007" | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Physician Member of the Arizona Medical Board 2007 to 2010 | Credentials | About page: "Physician Member, Arizona Medical Board, 2007-2010" | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Ophthalmology case reviewer for MAXIMUS 2010 to 2015 | Credentials | About page: "Ophthalmology Case Reviewer for MAXIMUS, 2010-2015" | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Clinical Assistant Professor, University of Arizona College of Medicine Phoenix | Credentials | About page | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Former Chief of Ophthalmology at Luke AFB and Scott AFB, US Air Force Medical Corps | Credentials | About page: Military experience | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
No history of malpractice settlements or verdicts, no medical board actions | Credentials | About page: Medical Liability | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
400+ cases completed | Credentials | Main expert witness page says 400+; the current state pages say 100+ | https://www.expertophthalmologywitness.com/ophthalmologist-expert-witness/ | Needs client confirmation
Dr. Lefkowitz has reviewed cases from Kentucky | Opening | Main expert witness page: list of states where he has reviewed cases | https://www.expertophthalmologywitness.com/ophthalmologist-expert-witness/ | Confirmed
Certificate of merit filed with the complaint; at least one qualified expert; reasonable basis | Kentucky rules, FAQ | KRS 411.167(1)-(2) | https://apps.legislature.ky.gov/law/statutes/statute.aspx?id=49312 | Confirmed
Certificate can be supplemented within 60 days of service | Kentucky rules | KRS 411.167(2)(b): "within sixty (60) days after service of the complaint" | https://apps.legislature.ky.gov/law/statutes/statute.aspx?id=49312 | Confirmed
Not due until 90 days after requested records are produced | Kentucky rules | KRS 411.167(5) | https://apps.legislature.ky.gov/law/statutes/statute.aspx?id=49312 | Confirmed
In force since June 2019 | Kentucky rules | 2019 Ky. Acts ch. 180, effective June 27, 2019 | https://apps.legislature.ky.gov/law/acts/19RS/documents/0180.pdf | Confirmed
One year to file, counted from discovery of the injury | Kentucky rules, FAQ | KRS 413.140(1)(e) and (2) | https://apps.legislature.ky.gov/law/statutes/statute.aspx?id=58050 | Confirmed
Depositions by phone or video; travel to Kentucky for trial | Services, FAQ | Current Kentucky page and site header text | https://www.expertophthalmologywitness.com/kentucky-expert-ophthalmology-witness/ | Confirmed
Case types: cataract, eyelid/oculoplastic, LASIK/refractive, glaucoma, retinal detachment, strabismus, pterygium, emergency care | Case types | About page practice specialties and the site's service pages | https://www.expertophthalmologywitness.com/about-me/ | Confirmed
Neighbouring states: Ohio, Indiana, Illinois, Missouri, Tennessee, Virginia, West Virginia | Nearby states | All seven border Kentucky and have a page on the site |  | Confirmed
Removed during the check because the site does not state them: "lens and wound problems" (cataract), "diagnosis and management" (glaucoma), "delayed diagnosis" (retinal detachment).

## Open Questions
Open Questions
Points that need a decision before or during the rollout
# | Topic | Question | Your answer
1 | Case count | The main expert witness page says 400+ cases; the current state pages say 100+. Which number is correct?
2 | Image alt text | The doctor photo and email icon have no alt text. They are shared images, so adding it updates every page that uses them. Should it be added?
3 | Site publisher name | The SEO plugin lists the website as published by a user called "admin" with a blank image, on every page. Should it show Dr. Lefkowitz instead?
4 | Rhode Island URL | The Rhode Island page address is spelled "rhose-island". Should it be corrected (with a redirect from the old address)?
5 | Missing states | 11 US states have no page yet (see Missing States). Should pages be created for them?
Yellow cells are for your answers.

## Missing States
US States With No Page
From the site's page sitemap
State | Listed on the main page as a state where cases were reviewed
Arkansas | Yes
Delaware | No
Iowa | No
Maine | No
Maryland | Yes
Nebraska | No
New Hampshire | No
North Dakota | No
South Carolina | No
Vermont | No
Wisconsin | Yes